## Dashboard
Software Development - Defect Dashboard | [8 empty] | from | 2009-06-08 | to | 2009-06-14 | 24
Defects actual week by type and severity
| Cosmetical | Minor | Major | Critical | Total
assigned | 1 | 19 | 17 | 3 | 40 | [6 empty] | Defect assigned fix pending
resolved | 0 | 4 | 7 | 1 | 12 | [6 empty] | Defect assigned, fix delivered, not yet retested
closed | 9 | 68 | 83 | 14 | 174 | [6 empty] | Defect assigned, fix delivered and successfully retested
Total | 10 | 91 | 107 | 18 | 226
Assigned, resolved and closed defects cumulated over the last 18 weeks | [7 empty] | New defects assigned, resolved and closed last 18 weeks - week on week
Average resolution / conclusion times in calendar days | [7 empty] | Average resolution / conclusion times in calendar days last 18 weeks
|  |  | Cosmetical | Minor | Major | Critical | Total
Assigned to resolved |  |  | 10.7778 | 16.6389 | 18.1556 | 9.1333 | 16.4839
Resolved to closed |  |  | 6.6667 | 14.1029 | 10.9759 | 5.2143 | 11.5115
Assigned to closed |  |  | 17.4444 | 30.6912 | 29.988 | 14.2857 | 28.3506

## Data
Data - List of Defects
Defect ID | Severity | State | Assigned on | Resolved on | Closed on
1 | Critical | closed | 2009-01-28 | 2009-01-28 | 2009-01-30
2 | Major | closed | 2009-01-29 | 2009-01-30 | 2009-01-31
3 | Major | closed | 2009-01-30 | 2009-02-12 | 2009-02-14
4 | Minor | closed | 2009-01-30 | 2009-02-14 | 2009-02-17
5 | Major | closed | 2009-01-30 | 2009-03-17 | 2009-04-01
6 | Minor | closed | 2009-01-31 | 2009-02-10 | 2009-02-11
7 | Minor | closed | 2009-01-31 | 2009-02-04 | 2009-03-27
8 | Minor | closed | 2009-02-03 | 2009-02-14 | 2009-07-14
9 | Minor | closed | 2009-02-06 | 2009-02-13 | 2009-02-17
10 | Minor | closed | 2009-02-07 | 2009-02-14 | 2009-03-06
11 | Major | closed | 2009-02-07 | 2009-02-28 | 2009-03-04
12 | Minor | closed | 2009-02-07 | 2009-03-05 | 2009-03-07
13 | Minor | closed | 2009-02-08 | 2009-02-13 | 2009-02-25
14 | Minor | closed | 2009-02-08 | 2009-02-28 | 2009-03-07
15 | Cosmetical | closed | 2009-02-10 | 2009-03-13 | 2009-03-14
16 | Major | closed | 2009-02-11 | 2009-02-28 | 2009-04-01
17 | Minor | closed | 2009-02-11 | 2009-02-13 | 2009-06-13
18 | Minor | closed | 2009-02-12 | 2009-02-13 | 2009-09-15
19 | Major | closed | 2009-02-12 | 2009-02-12 | 2009-07-08
20 | Cosmetical | closed | 2009-02-13 | 2009-02-18 | 2009-02-19
21 | Major | closed | 2009-02-13 | 2009-02-28 | 2009-03-03
22 | Major | closed | 2009-02-13 | 2009-02-20 | 2009-02-25
23 | Major | closed | 2009-02-13 | 2009-02-28 | 2009-03-05
24 | Major | closed | 2009-02-13 | 2009-02-14 | 2009-02-14
25 | Minor | closed | 2009-02-15 | 2009-04-07 | 2009-05-09
26 | Minor | closed | 2009-02-15 | 2009-04-07 | 2009-04-10
27 | Major | closed | 2009-02-17 | 2009-03-04 | 2009-03-07
28 | Minor | closed | 2009-02-18 | 2009-02-18 | 2009-02-19
29 | Minor | closed | 2009-02-19 | 2009-04-07 | 2009-04-12
30 | Minor | closed | 2009-02-19 | 2009-04-07 | 2009-06-30
31 | Major | closed | 2009-02-19 | 2009-04-07 | 2009-04-12
32 | Major | closed | 2009-02-19 | 2009-04-18 | 2009-04-18
33 | Cosmetical | closed | 2009-02-19 | 2009-02-20 | 2009-03-27
34 | Major | closed | 2009-02-19 | 2009-03-13 | 2009-03-20
35 | Minor | closed | 2009-02-19 | 2009-03-13 | 2009-04-17
36 | Major | closed | 2009-02-20 | 2009-03-13 | 2009-03-25
37 | Major | closed | 2009-02-20 | 2009-03-13 | 2009-05-05
38 | Major | closed | 2009-02-20 | 2009-04-14 | 2009-04-14
39 | Major | closed | 2009-02-21 | 2009-02-24 | 2009-02-24
40 | Major | closed | 2009-02-21 | 2009-04-03 | 2009-05-05
41 | Minor | closed | 2009-02-25 | 2009-03-13 | 2009-05-06
42 | Major | closed | 2009-02-25 | 2009-04-02 | 2009-04-16
43 | Minor | closed | 2009-02-25 | 2009-03-20 | 2009-03-27
44 | Major | closed | 2009-02-26 | 2009-03-13 | 2009-04-24
45 | Major | closed | 2009-02-26 | 2009-03-18 | 2009-04-01
46 | Minor | closed | 2009-02-26 | 2009-08-17 | 2009-09-18
47 | Major | closed | 2009-02-26 | 2009-02-26 | 2009-02-26
48 | Major | closed | 2009-02-27 | 2009-04-08 | 2009-05-01
49 | Minor | closed | 2009-02-27 | 2009-04-07 | 2009-04-22
50 | Major | closed | 2009-02-27 | 2009-03-24 | 2009-04-10
51 | Minor | closed | 2009-02-28 | 2009-03-07 | 2009-05-02
52 | Minor | closed | 2009-02-28 | 2009-03-13 | 2009-03-25
53 | Minor | closed | 2009-03-01 | 2009-03-13 | 2009-03-14
54 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
55 | Minor | closed | 2009-03-05 | 2009-03-20 | 2009-03-21
56 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
57 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
58 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
59 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
60 | Major | closed | 2009-03-05 | 2009-03-05 | 2009-03-05
61 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-04-10
62 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-04-10
63 | Minor | closed | 2009-03-06 | 2009-03-07 | 2009-03-07
64 | Minor | closed | 2009-03-06 | 2009-03-13 | 2009-03-25
65 | Minor | closed | 2009-03-06 | 2009-04-22 | 2009-04-29
66 | Major | closed | 2009-03-07 | 2009-04-03 | 2009-06-10
67 | Minor | closed | 2009-03-08 | 2009-07-10 | 2009-07-14
68 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
69 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
70 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
71 | Minor | closed | 2009-03-11 | 2009-03-21 | 2009-03-25
72 | Major | closed | 2009-03-11 | 2009-04-02 | 2009-04-15
73 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-04-24
74 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-04-18
75 | Minor | closed | 2009-03-11 | 2009-03-18 | 2009-03-25
76 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-05-01
77 | Major | closed | 2009-03-12 | 2009-03-17 | 2009-04-03
78 | Major | closed | 2009-03-13 | 2009-03-25 | 2009-03-25
79 | Major | closed | 2009-03-14 | 2009-04-02 | 2009-04-09
80 | Minor | closed | 2009-03-14 | 2009-07-10 | 2009-07-18
81 | Minor | closed | 2009-03-15 | 2009-03-16 | 2009-03-23
82 | Minor | closed | 2009-03-15 | 2009-03-16 | 2009-03-23
83 | Major | closed | 2009-03-15 | 2009-04-02 | 2009-04-30
84 | Critical | closed | 2009-03-15 | 2009-04-02 | 2009-04-24
85 | Major | closed | 2009-03-15 | 2009-04-22 | 2009-04-24
86 | Minor | closed | 2009-03-15 | 2009-04-08 | 2009-04-09
87 | Major | closed | 2009-03-18 | 2009-03-18 | 2009-03-18
88 | Minor | closed | 2009-03-18 | 2009-04-07 | 2009-06-13
89 | Major | closed | 2009-03-20 | 2009-04-02 | 2009-05-05
90 | Minor | closed | 2009-03-20 | 2009-04-03 | 2009-04-14
91 | Minor | closed | 2009-03-21 | 2009-04-03 | 2009-04-08
92 | Minor | closed | 2009-03-24 | 2009-04-07 | 2009-06-13
93 | Major | closed | 2009-03-25 | 2009-04-02 | 2009-04-08
94 | Critical | closed | 2009-03-25 | 2009-04-02 | 2009-04-16
95 | Major | closed | 2009-03-25 | 2009-04-03 | 2009-04-04
96 | Minor | closed | 2009-03-25 | 2009-04-02 | 2009-04-03
97 | Minor | closed | 2009-03-25 | 2009-04-18 | 2009-05-05
98 | Major | closed | 2009-03-27 | 2009-05-22 | 2009-05-23
99 | Major | closed | 2009-03-27 | 2009-04-02 | 2009-04-03
100 | Major | closed | 2009-03-27 | 2009-04-03 | 2009-04-17
101 | Minor | closed | 2009-03-28 | 2009-04-18 | 2009-04-22
102 | Major | closed | 2009-03-28 | 2009-04-08 | 2009-05-08
103 | Minor | closed | 2009-03-31 | 2009-04-07 | 2009-04-10
104 | Cosmetical | closed | 2009-04-01 | 2009-04-09 | 2009-04-23
105 | Critical | closed | 2009-04-03 | 2009-04-08 | 2009-04-09
106 | Minor | closed | 2009-04-05 | 2009-04-16 | 2009-04-17
107 | Major | closed | 2009-04-05 | 2009-04-24 | 2009-04-30
108 | Minor | closed | 2009-04-08 | 2009-05-12 | 2009-05-22
109 | Major | closed | 2009-04-08 | 2009-04-18 | 2009-04-22
110 | Minor | closed | 2009-04-08 | 2009-04-18 | 2009-04-22
111 | Major | closed | 2009-04-09 | 2009-07-15 | 2009-07-22
112 | Minor | closed | 2009-04-09 | 2009-04-18 | 2009-04-23
113 | Minor | closed | 2009-04-09 | 2009-04-18 | 2009-04-23
114 | Minor | closed | 2009-04-09 | 2009-04-16 | 2009-04-17
115 | Minor | closed | 2009-04-09 | 2009-05-22 | 2009-05-22
116 | Major | closed | 2009-04-10 | 2009-07-15 | 2009-08-18
117 | Major | closed | 2009-04-10 | 2009-04-10 | 2009-04-10
118 | Minor | closed | 2009-04-10 | 2009-05-15 | 2009-05-23
119 | Critical | closed | 2009-04-11 | 2009-04-18 | 2009-04-23
120 | Minor | closed | 2009-04-11 | 2009-05-01 | 2009-05-02
121 | Minor | closed | 2009-04-14 | 2009-05-22 | 2009-06-10
122 | Major | closed | 2009-04-14 | 2009-04-15 | 2009-04-24
123 | Major | closed | 2009-04-16 | 2009-04-22 | 2009-04-24
124 | Major | closed | 2009-04-16 | 2009-05-29 | 2009-05-30
125 | Critical | closed | 2009-04-16 | 2009-05-09 | 2009-05-14
126 | Minor | closed | 2009-04-16 | 2009-05-09 | 2009-05-13
127 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-09-19
128 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-05-07
129 | Minor | closed | 2009-04-17 | 2009-07-22 | 2009-09-19
130 | Major | closed | 2009-04-17 | 2009-05-09 | 2009-05-09
131 | Minor | closed | 2009-04-17 | 2009-05-05 | 2009-05-06
132 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-05-06
133 | Critical | closed | 2009-04-18 | 2009-05-22 | 2009-05-29
134 | Major | closed | 2009-04-22 | 2009-05-23 | 2009-06-02
135 | Major | closed | 2009-04-22 | 2009-05-23 | 2009-06-03
136 | Major | closed | 2009-04-22 | 2009-05-11 | 2009-05-13
137 | Major | closed | 2009-04-23 | 2009-05-23 | 2009-05-23
138 | Major | closed | 2009-04-23 | 2009-07-15 | 2009-07-22
139 | Major | closed | 2009-04-23 | 2009-05-22 | 2009-05-31
140 | Cosmetical | closed | 2009-04-24 | 2009-07-22 | 2009-07-30
141 | Minor | closed | 2009-04-25 | 2009-05-01 | 2009-05-01
142 | Minor | closed | 2009-04-29 | 2009-04-29 | 2009-04-29
143 | Minor | closed | 2009-04-30 | 2009-07-10 | 2009-07-10
144 | Minor | closed | 2009-04-30 | 2009-07-03 | 2009-07-19
145 | Minor | closed | 2009-04-30 | 2009-05-23 | 2009-05-23
146 | Minor | closed | 2009-04-30 | 2009-05-12 | 2009-06-03
147 | Major | closed | 2009-04-30 | 2009-05-22 | 2009-05-28
148 | Major | resolved | 2009-05-01 | 2009-05-22 | 2009-05-30
149 | Major | closed | 2009-05-01 | 2009-05-29 | 2009-06-09
150 | Minor | closed | 2009-05-01 | 2009-05-12 | 2009-06-06
151 | Major | closed | 2009-05-01 | 2009-05-22 | 2009-05-23
152 | Major | closed | 2009-05-02 | 2009-05-29 | 2009-05-30
153 | Major | closed | 2009-05-02 | 2009-05-21 | 2009-05-23
154 | Critical | closed | 2009-05-02 | 2009-05-06 | 2009-05-06
155 | Minor | closed | 2009-05-02 | 2009-05-29 | 2009-06-10
156 | Minor | closed | 2009-05-03 | 2009-05-12 | 2009-05-23
157 | Minor | closed | 2009-05-03 | 2009-05-09 | 2009-05-21
158 | Major | closed | 2009-05-03 | 2009-05-29 | 2009-07-01
159 | Major | closed | 2009-05-06 | 2009-05-22 | 2009-05-29
160 | Major | closed | 2009-05-06 | 2009-05-22 | 2009-05-23
161 | Major | closed | 2009-05-06 | 2009-05-23 | 2009-05-23
162 | Minor | closed | 2009-05-06 | 2009-07-10 | 2009-07-19
163 | Critical | closed | 2009-05-06 | 2009-05-09 | 2009-05-09
164 | Major | closed | 2009-05-07 | 2009-06-04 | 2009-06-10
165 | Minor | closed | 2009-05-07 | 2009-05-22 | 2009-06-02
166 | Major | closed | 2009-05-08 | 2009-05-22 | 2009-05-29
167 | Minor | closed | 2009-05-08 | 2009-07-24 | 2009-07-25
168 | Major | closed | 2009-05-08 | 2009-07-15 | 2009-07-22
169 | Critical | closed | 2009-05-09 | 2009-05-15 | 2009-05-22
170 | Critical | closed | 2009-05-09 | 2009-07-31 | 2009-08-12
171 | Cosmetical | closed | 2009-05-12 | 2009-05-29 | 2009-06-03
172 | Major | closed | 2009-05-13 | 2009-05-19 | 2009-05-21
173 | Minor | closed | 2009-05-14 | 2009-07-15 | 2009-10-01
174 | Cosmetical | closed | 2009-05-15 | 2009-06-10 | 2009-06-11
175 | Minor | closed | 2009-05-16 | 2009-06-29 | 2009-07-08
176 | Major | closed | 2009-05-19 | 2009-05-28 | 2009-07-30
177 | Major | closed | 2009-05-19 | 2009-05-22 | 2009-07-11
178 | Critical | closed | 2009-05-21 | 2009-07-15 | 2009-07-25
179 | Minor | closed | 2009-05-22 | 2009-06-04 | 2009-06-04
180 | Minor | closed | 2009-05-22 | 2009-07-15 | 2009-08-18
181 | Critical | closed | 2009-05-23 | 2009-05-29 | 2009-06-02
182 | Critical | closed | 2009-05-23 | 2009-05-29 | 2009-05-30
183 | Minor | closed | 2009-05-23 | 2009-05-30 | 2009-05-30
184 | Minor | closed | 2009-05-24 | 2009-09-01 | 2009-09-30
185 | Critical | closed | 2009-05-24 | 2009-05-30 | 2009-06-03
186 | Critical | closed | 2009-05-26 | 2009-05-27 | 2009-05-28
187 | Major | closed | 2009-05-26 | 2009-07-15 | 2009-07-22
188 | Major | closed | 2009-05-27 | 2009-06-04 | 2009-06-09
189 | Major | closed | 2009-05-27 | 2009-07-15 | 2009-07-22
190 | Minor | closed | 2009-05-27 | 2009-06-07 | 2009-07-08
191 | Critical | closed | 2009-05-28 | 2009-07-15 | 2009-07-23
192 | Major | closed | 2009-05-28 | 2009-05-30 | 2009-06-03
193 | Major | closed | 2009-05-28 | 2009-06-04 | 2009-06-10
194 | Major | closed | 2009-05-28 | 2009-06-10 | 2009-06-10
195 | Minor | closed | 2009-05-29 | 2009-10-21 | 2009-10-21
196 | Major | closed | 2009-05-29 | 2009-06-05 | 2009-06-06
197 | Major | closed | 2009-05-30 | 2009-07-22 | 2009-07-30
198 | Minor | closed | 2009-05-30 | 2009-05-31 | 2009-06-06
199 | Critical | closed | 2009-05-31 | 2009-06-10 | 2009-07-08
200 | Major | closed | 2009-06-02 | 2009-06-10 | 2009-06-13
201 | Major | closed | 2009-06-02 | 2009-06-07 | 2009-06-09
202 | Major | closed | 2009-06-02 | 2009-07-31 | 2009-09-12
203 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-10
204 | Minor | closed | 2009-06-03 | 2009-06-30 | 2009-07-10
205 | Minor | closed | 2009-06-03 | 2009-06-13 | 2009-06-13
206 | Major | closed | 2009-06-03 | 2009-06-04 | 2009-07-07
207 | Major | closed | 2009-06-03 | 2009-07-15 | 2009-07-28
208 | Minor | closed | 2009-06-03 | 2009-06-29 | 2009-07-01
209 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-11
210 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-11
211 | Minor | closed | 2009-06-04 | 2009-07-15 | 2009-08-18
212 | Major | closed | 2009-06-04 | 2009-06-04 | 2009-06-11
213 | Major | closed | 2009-06-04 | 2009-06-25 | 2009-07-03
214 | Minor | closed | 2009-06-04 | 2009-06-30 | 2009-06-30
215 | Major | closed | 2009-06-05 | 2009-06-10 | 2009-06-10
216 | Minor | closed | 2009-06-05 | 2009-07-22 | 2009-07-22
217 | Major | closed | 2009-06-09 | 2009-06-11 | 2009-06-11
218 | Major | closed | 2009-06-09 | 2009-07-15 | 2009-07-28
219 | Major | closed | 2009-06-10 | 2009-06-25 | 2009-07-04
220 | Major | closed | 2009-06-11 | 2009-06-19 | 2009-07-04
221 | Major | closed | 2009-06-11 | 2009-06-14 | 2009-07-25
222 | Major | closed | 2009-06-11 | 2009-06-25 | 2009-07-09
223 | Major | closed | 2009-06-11 | 2009-07-10 | 2009-07-16
224 | Major | closed | 2009-06-12 | 2009-07-03 | 2009-07-24
225 | Minor | closed | 2009-06-12 | 2009-07-21 | 2009-07-28
226 | Major | resolved | 2009-06-13 | 2009-07-23 | 2009-07-29
227 | Major | closed | 2009-06-18 | 2009-07-15 | 2009-07-28
228 | Major | closed | 2009-06-23 | 2009-07-03 | 2009-07-15
229 | Major | closed | 2009-06-23 | 2009-07-10 | 2009-07-16
230 | Minor | closed | 2009-06-23 | 2009-07-07 | 2009-07-08
231 | Major | closed | 2009-06-24 | 2009-07-15 | 2009-07-28
232 | Major | closed | 2009-06-24 | 2009-07-15 | 2009-07-25
233 | Major | closed | 2009-06-25 | 2009-07-24 | 2009-07-25
234 | Minor | closed | 2009-06-25 | 2009-07-03 | 2009-07-05
235 | Major | closed | 2009-06-25 | 2009-07-15 | 2009-07-24
236 | Major | closed | 2009-06-28 | 2009-06-29 | 2009-07-02
237 | Critical | closed | 2009-06-30 | 2009-07-03 | 2009-07-03
238 | Major | closed | 2009-07-02 | 2009-07-03 | 2009-07-18
239 | Major | closed | 2009-07-02 | 2009-07-03 | 2009-07-15
240 | Minor | closed | 2009-07-02 | 2009-07-03 | 2009-07-03
241 | Major | closed | 2009-07-03 | 2009-07-22 | 2009-07-25
242 | Minor | closed | 2009-07-03 | 2009-07-21 | 2009-07-28
243 | Major | closed | 2009-07-03 | 2009-07-18 | 2009-07-21
244 | Major | closed | 2009-07-04 | 2009-07-21 | 2009-08-04
245 | Minor | closed | 2009-07-04 | 2009-07-10 | 2009-07-15
246 | Minor | closed | 2009-07-07 | 2009-07-10 | 2009-07-12
247 | Cosmetical | closed | 2009-07-07 | 2009-07-21 | 2009-08-07
248 | Major | closed | 2009-07-07 | 2009-07-18 | 2009-07-24
249 | Minor | closed | 2009-07-07 | 2009-07-21 | 2009-08-12
250 | Minor | closed | 2009-07-07 | 2009-07-22 | 2009-07-25
251 | Major | closed | 2009-07-07 | 2009-07-18 | 2009-07-30
252 | Minor | closed | 2009-07-07 | 2009-07-21 | 2009-07-24
253 | Cosmetical | closed | 2009-07-09 | 2009-07-24 | 2009-08-07
254 | Major | closed | 2009-07-09 | 2009-07-18 | 2009-07-25
255 | Major | closed | 2009-07-10 | 2009-07-18 | 2009-07-28
256 | Major | closed | 2009-07-15 | 2009-07-31 | 2009-09-17
257 | Minor | closed | 2009-07-15 | 2009-08-07 | 2009-08-08
258 | Minor | closed | 2009-07-16 | 2009-08-15 | 2009-08-21
259 | Major | closed | 2009-07-16 | 2009-08-15 | 2009-09-03
260 | Major | closed | 2009-07-21 | 2009-07-31 | 2009-07-31
261 | Major | closed | 2009-07-21 | 2009-07-28 | 2009-08-13
262 | Minor | closed | 2009-07-22 | 2009-09-02 | 2009-09-20
263 | Major | closed | 2009-07-22 | 2009-08-07 | 2009-09-01
264 | Minor | closed | 2009-07-23 | 2009-08-05 | 2009-09-04
265 | Major | resolved | 2009-07-23 | 2009-09-02 | 2009-09-10
266 | Major | resolved | 2009-07-23 | 2009-09-02 | 2009-09-09
267 | Minor | closed | 2009-07-23 | 2009-07-29 | 2009-07-30
268 | Major | closed | 2009-07-23 | 2009-07-29 | 2009-07-31
269 | Cosmetical | closed | 2009-07-24 | 2009-08-05 | 2009-08-08
270 | Minor | closed | 2009-07-25 | 2009-08-05 | 2009-08-12
271 | Minor | closed | 2009-07-25 | 2009-09-03 | 2009-09-11
272 | Minor | closed | 2009-07-25 | 2009-08-05 | 2009-09-11
273 | Major | closed | 2009-07-29 | 2009-08-15 | 2009-08-25
274 | Minor | closed | 2009-07-29 | 2009-09-02 | 2009-09-24
275 | Minor | closed | 2009-07-30 | 2009-07-30 | 2009-07-30
276 | Major | closed | 2009-07-30 | 2009-08-06 | 2009-09-16
277 | Major | closed | 2009-08-01 | 2009-08-21 | 2009-09-08
278 | Cosmetical | closed | 2009-08-01 | 2009-08-07 | 2009-08-11
279 | Critical | closed | 2009-08-01 | 2009-08-06 | 2009-08-13
280 | Major | closed | 2009-08-05 | 2009-09-12 | 2009-09-29
281 | Major | closed | 2009-08-05 | 2009-08-15 | 2009-08-25
282 | Major | closed | 2009-08-05 | 2009-09-01 | 2009-10-02
283 | Major | closed | 2009-08-06 | 2009-10-08 | 2009-10-17
284 | Major | closed | 2009-08-08 | 2009-08-17 | 2009-08-26
285 | Major | closed | 2009-08-08 | 2009-08-11 | 2009-08-26
286 | Minor | closed | 2009-08-08 | 2009-09-08 | 2009-10-02
287 | Critical | closed | 2009-08-11 | 2009-08-13 | 2009-09-03
288 | Minor | closed | 2009-08-12 | 2009-08-18 | 2009-09-08
289 | Major | closed | 2009-08-14 | 2009-09-30 | 2009-10-02
290 | Major | closed | 2009-08-15 | 2009-08-19 | 2009-08-26
291 | Critical | closed | 2009-08-15 | 2009-08-16 | 2009-08-18
292 | Major | closed | 2009-08-18 | 2009-10-07 | 2009-10-09
293 | Major | closed | 2009-08-18 | 2009-10-08 | 2009-10-17
294 | Major | closed | 2009-08-18 | 2009-09-05 | 2009-09-22
295 | Major | closed | 2009-08-19 | 2009-09-26 | 2009-09-29
296 | Minor | closed | 2009-08-19 | 2009-09-06 | 2009-09-22
297 | Minor | closed | 2009-08-21 | 2009-09-02 | 2009-09-10
298 | Major | closed | 2009-08-22 | 2009-10-14 | 2009-10-21
299 | Major | closed | 2009-08-22 | 2009-09-06 | 2009-09-23
300 | Major | closed | 2009-08-26 | 2009-08-27 | 2009-08-27
301 | Minor | closed | 2009-08-26 | 2009-08-28 | 2009-09-04
302 | Minor | closed | 2009-08-26 | 2009-09-11 | 2009-10-01
303 | Major | closed | 2009-08-26 | 2009-09-01 | 2009-09-04
304 | Major | assigned | 2009-08-26 | 2009-09-03 | 2009-09-09
305 | Cosmetical | resolved | 2009-08-29 | 2009-10-14 | 2009-10-21
306 | Major | closed | 2009-08-29 | 2009-09-05 | 2009-10-02
307 | Major | closed | 2009-09-01 | 2009-10-14 | 2009-10-21
308 | Minor | closed | 2009-09-03 | 2009-10-14 | 2009-10-20
309 | Cosmetical | assigned | 2009-09-03 | 2009-09-15 | 2009-09-21
310 | Minor | closed | 2009-09-05 | 2009-09-26 | 2009-09-27
311 | Major | closed | 2009-09-05 | 2009-09-18 | 2009-09-23
312 | Minor | assigned | 2009-09-06 | 2009-09-14 | 2009-09-23
313 | Minor | closed | 2009-09-08 | 2009-09-11 | 2009-09-23
314 | Minor | closed | 2009-09-08 | 2009-09-11 | 2009-09-11
315 | Minor | closed | 2009-09-08 | 2009-09-18 | 2009-09-24
316 | Major | resolved | 2009-09-08 | 2009-10-14 | 2009-10-21
317 | Major | closed | 2009-09-09 | 2009-09-22 | 2009-09-30
318 | Cosmetical | closed | 2009-09-09 | 2009-09-16 | 2009-09-26
319 | Major | closed | 2009-09-10 | 2009-09-18 | 2009-09-19
320 | Major | closed | 2009-09-10 | 2009-09-18 | 2009-09-19
321 | Minor | closed | 2009-09-10 | 2009-09-23 | 2009-09-24
322 | Major | closed | 2009-09-10 | 2009-09-23 | 2009-10-02
323 | Major | closed | 2009-09-11 | 2009-09-20 | 2009-09-29
324 | Minor | closed | 2009-09-11 | 2009-09-18 | 2009-09-24
325 | Minor | closed | 2009-09-11 | 2009-09-20 | 2009-10-03
326 | Minor | closed | 2009-09-11 | 2009-09-11 | 2009-10-01
327 | Minor | closed | 2009-09-11 | 2009-09-18 | 2009-09-29
328 | Major | closed | 2009-09-12 | 2009-09-23 | 2009-10-01
329 | Major | closed | 2009-09-13 | 2009-09-21 | 2009-10-01
330 | Major | assigned | 2009-09-13 | 2009-09-23 | 2009-09-30
331 | Cosmetical | closed | 2009-09-13 | 2009-09-22 | 2009-09-26
332 | Cosmetical | closed | 2009-09-15 | 2009-09-25 | 2009-09-29
333 | Minor | closed | 2009-09-16 | 2009-09-30 | 2009-10-03
334 | Major | closed | 2009-09-16 | 2009-09-26 | 2009-09-30
335 | Minor | closed | 2009-09-16 | 2009-09-23 | 2009-09-25
336 | Minor | resolved | 2009-09-16 | 2009-10-14 | 2009-10-23
337 | Major | resolved | 2009-09-16 | 2009-10-14 | 2009-10-20
338 | Major | closed | 2009-09-17 | 2009-09-26 | 2009-09-30
339 | Major | closed | 2009-09-17 | 2009-09-23 | 2009-09-23
340 | Major | closed | 2009-09-18 | 2009-10-14 | 2009-10-17
341 | Minor | closed | 2009-09-18 | 2009-09-25 | 2009-09-26
342 | Minor | assigned | 2009-09-19 | 2009-09-29 | 2009-10-05
343 | Minor | closed | 2009-09-19 | 2009-09-26 | 2009-10-02
344 | Major | resolved | 2009-09-19 | 2009-10-14 | 2009-10-23
345 | Minor | resolved | 2009-09-19 | 2009-10-14 | 2009-10-19
346 | Major | closed | 2009-09-20 | 2009-09-26 | 2009-09-27
347 | Minor | closed | 2009-09-22 | 2009-09-25 | 2009-10-03
348 | Minor | closed | 2009-09-23 | 2009-09-26 | 2009-09-30
349 | Minor | closed | 2009-09-24 | 2009-09-24 | 2009-09-24
350 | Major | closed | 2009-09-25 | 2009-09-30 | 2009-10-03
351 | Cosmetical | closed | 2009-09-25 | 2009-09-26 | 2009-09-29
352 | Major | resolved | 2009-09-25 | 2009-10-14 | 2009-10-22
353 | Major | resolved | 2009-09-25 | 2009-10-14 | 2009-10-19
354 | Minor | closed | 2009-09-26 | 2009-10-15 | 2009-10-20
355 | Major | resolved | 2009-09-26 | 2009-10-14 | 2009-10-19
356 | Major | closed | 2009-09-29 | 2009-10-14 | 2009-10-28
357 | Major | closed | 2009-09-30 | 2009-10-14 | 2009-10-17
358 | Minor | resolved | 2009-09-30 | 2009-10-14 | 2009-10-20
359 | Minor | closed | 2009-10-01 | 2009-10-14 | 2009-10-17
360 | Cosmetical | closed | 2009-10-02 | 2009-10-21 | 2009-10-22
361 | Major | resolved | 2009-10-02 | 2009-10-23 | 2009-10-29
362 | Major | resolved | 2009-10-02 | 2009-10-23 | 2009-10-29
363 | Minor | resolved | 2009-10-02 | 2009-10-17 | 2009-10-27
364 | Minor | resolved | 2009-10-02 | 2009-10-15 | 2009-10-22
365 | Major | closed | 2009-10-02 | 2009-10-04 | 2009-10-09
366 | Minor | resolved | 2009-10-03 | 2009-10-14 | 2009-10-24
367 | Minor | resolved | 2009-10-03 | 2009-10-14 | 2009-10-21
368 | Minor | resolved | 2009-10-03 | 2009-10-03 | 2009-10-11
369 | Cosmetical | assigned | 2009-10-06 | 2009-10-15 | 2009-10-20
370 | Major | closed | 2009-10-08 | 2009-10-20 | 2009-11-03
371 | Major | resolved | 2009-10-08 | 2009-10-20 | 2009-10-25
372 | Minor | resolved | 2009-10-09 | 2009-10-24 | 2009-11-01
373 | Minor | resolved | 2009-10-09 | 2009-10-20 | 2009-10-30
374 | Major | closed | 2009-10-09 | 2009-10-21 | 2009-10-22
375 | Cosmetical | resolved | 2009-10-13 | 2009-10-24 | 2009-11-01
376 | Minor | resolved | 2009-10-13 | 2009-10-23 | 2009-10-29
377 | Minor | closed | 2009-10-15 | 2009-10-21 | 2009-10-22
378 | Major | assigned | 2009-10-16 | 2009-10-23 | 2009-10-28
379 | Major | assigned | 2009-10-16 | 2009-10-24 | 2009-11-02
380 | Minor | closed | 2009-10-20 | 2009-10-23 | 2009-10-30
381 | Cosmetical | assigned | 2009-10-20 | 2009-10-29 | 2009-11-08
382 | Major | assigned | 2009-10-21 | 2009-11-01 | 2009-11-08
383 | Minor | assigned | 2009-10-21 | 2009-11-01 | 2009-11-10
384 | Major | closed | 2009-10-21 | 2009-10-22 | 2009-10-28
385 | Major | assigned | 2009-10-22 | 2009-11-02 | 2009-11-08
386 | Minor | assigned | 2009-10-23 | 2009-10-30 | 2009-11-04
387 | Minor | assigned | 2009-10-23 | 2009-10-30 | 2009-11-09
388 | Major | assigned | 2009-10-24 | 2009-10-31 | 2009-11-10
389 | Major | assigned | 2009-10-24 | 2009-09-02 | 2009-09-09
390 | Major | resolved | 2009-10-27 | 2009-11-03 | 2009-11-13
391 | Major | assigned | 2009-10-27 | 2009-11-08 | 2009-11-13
392 | Major | assigned | 2009-10-28 | 2009-11-09 | 2009-11-17
393 | Minor | assigned | 2009-10-28 | 2009-11-08 | 2009-11-18
394 | Minor | resolved | 2009-10-28 | 2009-10-28 | 2009-11-04
395 | Minor | assigned | 2009-10-28 | 2009-11-07 | 2009-11-16
396 | Major | closed | 2009-10-28 | 2009-10-30 | 2009-10-30
397 | Major | assigned | 2009-10-28 | 2009-11-07 | 2009-11-13
398 | Major | assigned | 2009-10-28 | 2009-11-07 | 2009-11-13
399 | Major | assigned | 2009-10-30 | 2009-10-16 | 2009-10-24
400 | Minor | assigned | 2009-10-30 | 2009-11-10 | 2009-11-17
401 | Minor | assigned | 2009-10-30 | 2009-11-09 | 2009-11-18
402 | Minor | assigned | 2009-11-03 | 2009-11-13 | 2009-11-22
403 | Major | assigned | 2009-11-03 | 2009-11-15 | 2009-11-25
404 | Minor | assigned | 2009-11-03 | 2009-11-14 | 2009-11-23
405 | Major | assigned | 2009-11-03 | 2009-11-13 | 2009-11-20
406 | Critical | assigned | 2009-11-03 | 2009-11-14 | 2009-11-22
407 | Minor | assigned | 2009-11-03 | 2009-11-12 | 2009-11-21
408 | Minor | assigned | 2009-11-03 | 2009-11-10 | 2009-11-15
409 | Minor | assigned | 2009-11-03 | 2009-11-11 | 2009-11-18
410 | Minor | assigned | 2009-11-03 | 2009-11-10 | 2009-11-17
411 | Minor | assigned | 2009-11-03 | 2009-11-15 | 2009-11-21
412 | Minor | assigned | 2009-11-03 | 2009-11-11 | 2009-11-17
413 | Major | assigned | 2009-11-03 | 2009-11-13 | 2009-11-21
414 | Minor | assigned | 2009-11-04 | 2009-11-16 | 2009-11-26
415 | Major | assigned | 2009-11-04 | 2009-11-12 | 2009-11-21

## Control
Control and Caluclations
Selected Week # | 23
Last Date | 2009-11-26
Last Sunday | 2009-11-29
Latest week | 48
Monday selected week | 2009-06-08
Sunday selected week | 2009-06-14
Selected week | 24
| Cosmetical | Minor | Major | Critical | Total
assigned | 1 | 19 | 17 | 3 | 40
resolved | 0 | 4 | 7 | 1 | 12
closed | 9 | 68 | 83 | 14 | 174
Total | 10 | 91 | 107 | 18 | 226
Week | Start | End | Assigned | Resolved | Closed | Assigned cumulated | Resolved cumulated | Closed cumulated | Assigned to resolved | Resolved to closed | Assigned to closed | Assigned to resolved | Resolved to closed | Assigned to closed
7 | 2009-02-09 | 2009-02-15 | 12 | 11 | 3 | 26 | 14 | 5 | 5.5 | 1.2 | 6.2 | 5.5 | 1.2 | 6.2
8 | 2009-02-16 | 2009-02-22 | 14 | 4 | 4 | 40 | 18 | 9 | 5 | 1.6667 | 7.4444 | 5 | 1.6667 | 7.4444
9 | 2009-02-23 | 2009-03-01 | 13 | 7 | 4 | 53 | 25 | 13 | 7.24 | 2.4615 | 7.6154 | 7.24 | 2.4615 | 7.6154
10 | 2009-03-02 | 2009-03-08 | 14 | 5 | 9 | 67 | 30 | 22 | 7.6667 | 3.4545 | 11.9545 | 7.6667 | 3.4545 | 11.9545
11 | 2009-03-09 | 2009-03-15 | 19 | 13 | 5 | 86 | 43 | 27 | 9.7442 | 3 | 11.8519 | 9.7442 | 3 | 11.8519
12 | 2009-03-16 | 2009-03-22 | 5 | 10 | 3 | 91 | 53 | 30 | 10.3208 | 2.9667 | 12.1667 | 10.3208 | 2.9667 | 12.1667
13 | 2009-03-23 | 2009-03-29 | 11 | 2 | 11 | 102 | 55 | 41 | 10.6182 | 5.9268 | 15.0976 | 10.6182 | 5.9268 | 15.0976
14 | 2009-03-30 | 2009-04-05 | 5 | 16 | 7 | 107 | 71 | 48 | 11.9859 | 6.75 | 16.8958 | 11.9859 | 6.75 | 16.8958
15 | 2009-04-06 | 2009-04-12 | 13 | 25 | 13 | 120 | 96 | 61 | 16.3958 | 6.2787 | 19.377 | 16.3958 | 6.2787 | 19.377
16 | 2009-04-13 | 2009-04-19 | 13 | 12 | 11 | 133 | 108 | 72 | 16.6111 | 6.9028 | 21.6806 | 16.6111 | 6.9028 | 21.6806
17 | 2009-04-20 | 2009-04-26 | 8 | 4 | 14 | 141 | 112 | 86 | 17 | 7.5233 | 22.4302 | 17 | 7.5233 | 22.4302
18 | 2009-04-27 | 2009-05-03 | 17 | 6 | 9 | 158 | 118 | 95 | 16.7119 | 8.3368 | 23.7684 | 16.7119 | 8.3368 | 23.7684
19 | 2009-05-04 | 2009-05-10 | 12 | 7 | 13 | 170 | 125 | 108 | 16.568 | 9.7685 | 25.6759 | 16.568 | 9.7685 | 25.6759
20 | 2009-05-11 | 2009-05-17 | 5 | 7 | 3 | 175 | 132 | 111 | 16.6439 | 9.6036 | 25.6667 | 16.6439 | 9.6036 | 25.6667
21 | 2009-05-18 | 2009-05-24 | 10 | 20 | 14 | 185 | 152 | 125 | 17.6447 | 8.968 | 25.8 | 17.6447 | 8.968 | 25.8
22 | 2009-05-25 | 2009-05-31 | 14 | 14 | 11 | 199 | 166 | 136 | 17.3976 | 8.5956 | 25.6838 | 17.3976 | 8.5956 | 25.6838
23 | 2009-06-01 | 2009-06-07 | 17 | 9 | 12 | 216 | 175 | 148 | 16.96 | 8.5946 | 25.3243 | 16.96 | 8.5946 | 25.3243
24 | 2009-06-08 | 2009-06-14 | 10 | 11 | 26 | 226 | 186 | 174 | 16.4839 | 11.5115 | 28.3506 | 16.4839 | 11.5115 | 28.3506
| Cosmetical | Minor | Major | Critical | Total
Assigned to resolved | 10.7778 | 16.6389 | 18.1556 | 9.1333 | 16.4839
Resolved to closed | 6.6667 | 14.1029 | 10.9759 | 5.2143 | 11.5115
Assigned to closed | 17.4444 | 30.6912 | 29.988 | 14.2857 | 28.3506
Week ISO 8601 | Start | End
2 | 2009-01-05 | 2009-01-11
3 | 2009-01-12 | 2009-01-18
4 | 2009-01-19 | 2009-01-25
5 | 2009-01-26 | 2009-02-01
6 | 2009-02-02 | 2009-02-08
7 | 2009-02-09 | 2009-02-15
8 | 2009-02-16 | 2009-02-22
9 | 2009-02-23 | 2009-03-01
10 | 2009-03-02 | 2009-03-08
11 | 2009-03-09 | 2009-03-15
12 | 2009-03-16 | 2009-03-22
13 | 2009-03-23 | 2009-03-29
14 | 2009-03-30 | 2009-04-05
15 | 2009-04-06 | 2009-04-12
16 | 2009-04-13 | 2009-04-19
17 | 2009-04-20 | 2009-04-26
18 | 2009-04-27 | 2009-05-03
19 | 2009-05-04 | 2009-05-10
20 | 2009-05-11 | 2009-05-17
21 | 2009-05-18 | 2009-05-24
22 | 2009-05-25 | 2009-05-31
23 | 2009-06-01 | 2009-06-07
24 | 2009-06-08 | 2009-06-14
25 | 2009-06-15 | 2009-06-21
26 | 2009-06-22 | 2009-06-28
27 | 2009-06-29 | 2009-07-05
28 | 2009-07-06 | 2009-07-12
29 | 2009-07-13 | 2009-07-19
30 | 2009-07-20 | 2009-07-26
31 | 2009-07-27 | 2009-08-02
32 | 2009-08-03 | 2009-08-09
33 | 2009-08-10 | 2009-08-16
34 | 2009-08-17 | 2009-08-23
35 | 2009-08-24 | 2009-08-30
36 | 2009-08-31 | 2009-09-06
37 | 2009-09-07 | 2009-09-13
38 | 2009-09-14 | 2009-09-20
39 | 2009-09-21 | 2009-09-27
40 | 2009-09-28 | 2009-10-04
41 | 2009-10-05 | 2009-10-11
42 | 2009-10-12 | 2009-10-18
43 | 2009-10-19 | 2009-10-25
44 | 2009-10-26 | 2009-11-01
45 | 2009-11-02 | 2009-11-08
46 | 2009-11-09 | 2009-11-15
47 | 2009-11-16 | 2009-11-22
48 | 2009-11-23 | 2009-11-29
49 | 2009-11-30 | 2009-12-06
50 | 2009-12-07 | 2009-12-13
51 | 2009-12-14 | 2009-12-20
52 | 2009-12-21 | 2009-12-27
53 | 2009-12-28 | 2010-01-03
Formulas:
Cosmetical = [Minor]-6
Cosmetical = [Minor, row above]+1
Minor = [Minor, row below]-7
Minor = [Cosmetical]+6