## Pivot Table Risks
Risk Matrix |  |  | "Pivot Tables" with texts in the value area - formula version |  | www.clearlyandsimply.com
Type
Probability
|  | Low | Medium | High | Very high
Impact | Low | Environmental clearance for staging or borrow sites required | Hazardous waste site analysis incomplete | Unanticipated cumulative impact issues | Historic site, endangered species, riparian areas, wetlands and/or public park present
|  | Unforeseen formal Section 7 consultation is required | Landowners unwilling to sell | Inaccurate assumptions on technical issues in planning stage | Design changes require additional Environmental analysis
|  | Project may encroach into the Coastal Zone | Changes to storm-water requirements | Bridge site data incomplete to DES | Project may encroach onto a Scenic Highway
|  | Controversy on environmental grounds expected | Pressure to deliver project on an accelerated schedule | Threat of lawsuits | Project may encroach into a floodplain or a regulatory floodway
|  | Foundation and geotechnical tasks (foundation drilling and material testing) not identified and included in project workplan | Unexpected environmental constraints that impact bridge construction | Piles driven into fish habitat may require special noise attenuation to protect marine species | New information required for permits
|  | Discovery of hazardous waste in the right of way phase | Inaccurate contract time estimates | Condition of the bridge deck unknown | Delay due to permits or agreements, from Federal, State, or local agencies for geotechnical subsurface exploration
|  | Underestimated support resources or overly optimistic delivery schedule | Unidentified utilities | For projects involving bridge removal, bridge carries traffic during staging | Temporary construction easements expire
|  | Lack of specialized staff (biology, anthropology, geotechnical, archeology, etc.) | Experimental or research features incorporated | Verify that all seasonal constraints and permitting requirements are identified and incorporated in the project schedule | Electrical power lines not seen and in conflict with construction
|  |  | No control over staff priorities | Unforeseen aesthetic requirements | Unplanned work that must be accommodated
|  |  |  | Unforeseen railroad involvement | Unresolved project conflicts not escalated in a timely manner
|  |  |  | Project scope definition is incomplete | Local agency support not attained
|  |  |  | Consultant or contractor delays | Inconsistent cost, time, scope and quality objectives
|  |  |  | Estimating and/or scheduling errors | Overlapping of one or more project limits, scope of work or schedule
Inexperienced staff assigned
Functional units not available, overloaded
| Medium | Unexpected Section 106 issues expected | Unresolved constructability items | Unforeseen formal NEPA/404 consultation is required | Availability of project data and mapping at the beginning of the environmental study is insufficient
|  | Unanticipated noise impacts | Political factors or support for project changes | Project may encroach to a Wild and Scenic River | Unforeseen construction window and/or rainy season requirements
|  | Design incomplete | Increase in material cost due to market forces | Unreasonably high expectations from stakeholders | Dewatering is required due to change in water table
|  | Project in a critical water shortage area and a water source agreement required | Bridges constructed at grade and then excavated underneath may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Water quality regulations change | Unexpected paleontology findings
|  | Bridge is a habitat to bats or other species requiring mitigation or seasonal construction | Access to adjacent properties is necessary to resolve constructability requirements | Foundations utilizing Cast-In-Drilled-Hole or Cast-In-Steel-Shell pile 30” in diameter or greater may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Priorities change on existing program
|  | Complex structures hydraulic design requiring investigation and planning | Delay due to Right-of-Entry agreements for geotechnical subsurface exploration | Hazardous materials in existing structure or surrounding soil; lead paint, contaminated soil, asbestos pipe, asbestos bearings and shims | Inconsistent cost, time, scope, and quality objectives
|  | Acquisition of parcels controlled by a State or Federal Agency may take longer than anticipated | Right of Way datasheet incomplete or underestimated | Delay due to traffic management and lane closure for geotechnical subsurface exploration | Funding changes for fiscal year
|  | Seasonal requirements during utility relocation | Utility company workload, financial condition or timeline | Project scope, schedule, objectives, cost, and deliverables are not clearly defined or understood
|  | Expired temporary construction easements | Inadequate pool of expert witnesses or qualified appraisers | Unforeseen agreements required
|  | Permit work window time is insufficient | Lack of coordination/communication | Lack of understanding of complex internal funding procedures
Buried man-made objects/unidentified hazardous waste
Changes during construction require additional coordination with resource agencies
Late discovery of aerially deposited lead
Unanticipated project manager workload
Capital funding unavailable for right of way or construction
| High | New alternatives required to avoid, mitigate or minimize impact | Acquisition, creation or restoration of on or off-site mitigation | Project does not conform to the state implementation plan for air quality at the program and plan level | Environmental analysis incomplete
|  | Unforeseen Section 4(f) resources affected | Unexpected Native American concerns | Unexpected geotechnical or groundwater issues | New information after Environmental Document is completed may require re-evaluation or a new document (i.e. utility relocation beyond document coverage)
|  | Changes to materials/geotechnical/foundation | Project causes an unanticipated barrier to wildlife | Consultant design not up to Department standards | Unforeseen design exceptions required
|  | Stakeholders request late changes | Surveys incomplete | Unable to meet Americans with Disabilities Act requirements | Complex hydraulic features
|  | New permits or additional information required | New stakeholders emerge and request changes | Reviewing agency requires longer than expected review time | Incomplete quantity estimates
|  | Special railroad requirements are necessary including an extensive geotechnical report for temporary shoring system adjacent to tracks | Permits or agency actions delayed or take longer than expected | Labor shortage or strike | New or revised design standard
|  | Existing structures planned for modification not evaluated for seismic retrofit, scour potential and structural capacity | Environmental regulations change | Change requests due to differing site conditions | Local communities pose objections
|  | Assumptions upon which the Advance Planning Study is based on are realistic and verification of these assumptions prior to completion of the Project Report | Design changes to alignment, profile, typical cross section, stage construction between Advance Planning Study and the Bridge Site Submittal | Delay in demolition due to sensitive habitat requirements or other reasons | Construction or pile driving noise and vibration impacting adjacent businesses or residents
|  | Utility relocation requires more time than planned | Resolving objections to Right of Way appraisal takes more time and/or money | Added workload or time requirements because of new direction, policy, or statute | Temporary excavation and shoring system design is not adequate
|  | Street or ramp closures not coordinated with local community | Need for “Permits to Enter” not considered in project schedule development | Losing critical staff at crucial point of the project | Falsework design is not adequate
|  | Insufficient or limited construction or staging areas | Condemnation process takes longer than anticipated | Priorities change on existing program | Scope creep
|  | Long lead time for utilities caused by design and manufacture of special components (steel towers or special pipe) | Project purpose and need is not well-defined
|  | Delay in earlier project phases jeopardizes ability to meet programmed delivery commitment | Unanticipated escalation in right of way values or construction cost
|  | Insufficient time to plan | Public awareness/campaign not planned
Internal “red tape” causes delay getting approvals, decisions

## Risk List
Risk List
# | Risk | Type | Impact | Probability
1 | Environmental analysis incomplete | Environmental Risks | High | Very high
2 | Availability of project data and mapping at the beginning of the environmental study is insufficient | Environmental Risks | Medium | Very high
3 | New information after Environmental Document is completed may require re-evaluation or a new document (i.e. utility relocation beyond document coverage) | Environmental Risks | High | Very high
4 | New alternatives required to avoid, mitigate or minimize impact | Environmental Risks | High | Low
5 | Acquisition, creation or restoration of on or off-site mitigation | Environmental Risks | High | Medium
6 | Environmental clearance for staging or borrow sites required | Environmental Risks | Low | Low
7 | Historic site, endangered species, riparian areas, wetlands and/or public park present | Environmental Risks | Low | Very high
8 | Design changes require additional Environmental analysis | Environmental Risks | Low | Very high
9 | Unforeseen formal NEPA/404 consultation is required | Environmental Risks | Medium | High
10 | Unforeseen formal Section 7 consultation is required | Environmental Risks | Low | Low
11 | Unexpected Section 106 issues expected | Environmental Risks | Medium | Low
12 | Unexpected Native American concerns | Environmental Risks | High | Medium
13 | Unforeseen Section 4(f) resources affected | Environmental Risks | High | Low
14 | Project may encroach into the Coastal Zone | Environmental Risks | Low | Low
15 | Project may encroach onto a Scenic Highway | Environmental Risks | Low | Very high
16 | Project may encroach to a Wild and Scenic River | Environmental Risks | Medium | High
17 | Unanticipated noise impacts | Environmental Risks | Medium | Low
18 | Project causes an unanticipated barrier to wildlife | Environmental Risks | High | Medium
19 | Project may encroach into a floodplain or a regulatory floodway | Environmental Risks | Low | Very high
20 | Project does not conform to the state implementation plan for air quality at the program and plan level | Environmental Risks | High | High
21 | Unanticipated cumulative impact issues | Environmental Risks | Low | High
22 | Design incomplete | Design Risks | Medium | Low
23 | Unexpected geotechnical or groundwater issues | Design Risks | High | High
24 | Inaccurate assumptions on technical issues in planning stage | Design Risks | Low | High
25 | Surveys incomplete | Design Risks | High | Medium
26 | Changes to materials/geotechnical/foundation | Design Risks | High | Low
27 | Bridge site data incomplete to DES | Design Risks | Low | High
28 | Hazardous waste site analysis incomplete | Design Risks | Low | Medium
29 | Unforeseen design exceptions required | Design Risks | High | Very high
30 | Consultant design not up to Department standards | Design Risks | High | High
31 | Unresolved constructability items | Design Risks | Medium | Medium
32 | Complex hydraulic features | Design Risks | High | Very high
33 | Unable to meet Americans with Disabilities Act requirements | Design Risks | High | High
34 | Project in a critical water shortage area and a water source agreement required | Design Risks | Medium | Low
35 | Incomplete quantity estimates | Design Risks | High | Very high
36 | Unforeseen construction window and/or rainy season requirements | Design Risks | Medium | Very high
37 | New or revised design standard | Design Risks | High | Very high
38 | Landowners unwilling to sell | External Risks | Low | Medium
39 | Local communities pose objections | External Risks | High | Very high
40 | Unreasonably high expectations from stakeholders | External Risks | Medium | High
41 | Political factors or support for project changes | External Risks | Medium | Medium
42 | Stakeholders request late changes | External Risks | High | Low
43 | New stakeholders emerge and request changes | External Risks | High | Medium
44 | Threat of lawsuits | External Risks | Low | High
45 | Increase in material cost due to market forces | External Risks | Medium | Medium
46 | Water quality regulations change | External Risks | Medium | High
47 | New permits or additional information required | External Risks | High | Low
48 | Reviewing agency requires longer than expected review time | External Risks | High | High
49 | Changes to storm-water requirements | External Risks | Low | Medium
50 | Permits or agency actions delayed or take longer than expected | External Risks | High | Medium
51 | New information required for permits | External Risks | Low | Very high
52 | Environmental regulations change | External Risks | High | Medium
53 | Controversy on environmental grounds expected | External Risks | Low | Low
54 | Pressure to deliver project on an accelerated schedule | External Risks | Low | Medium
55 | Labor shortage or strike | External Risks | High | High
56 | Construction or pile driving noise and vibration impacting adjacent businesses or residents | External Risks | High | Very high
57 | Foundations utilizing Cast-In-Drilled-Hole or Cast-In-Steel-Shell pile 30” in diameter or greater may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Engineering Services Risks | Medium | High
58 | Bridges constructed at grade and then excavated underneath may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Engineering Services Risks | Medium | Medium
59 | Hazardous materials in existing structure or surrounding soil; lead paint, contaminated soil, asbestos pipe, asbestos bearings and shims | Engineering Services Risks | Medium | High
60 | Piles driven into fish habitat may require special noise attenuation to protect marine species | Engineering Services Risks | Low | High
61 | Special railroad requirements are necessary including an extensive geotechnical report for temporary shoring system adjacent to tracks | Engineering Services Risks | High | Low
62 | Access to adjacent properties is necessary to resolve constructability requirements | Engineering Services Risks | Medium | Medium
63 | Existing structures planned for modification not evaluated for seismic retrofit, scour potential and structural capacity | Engineering Services Risks | High | Low
64 | Foundation and geotechnical tasks (foundation drilling and material testing) not identified and included in project workplan | Engineering Services Risks | Low | Low
65 | Bridge is a habitat to bats or other species requiring mitigation or seasonal construction | Engineering Services Risks | Medium | Low
66 | Condition of the bridge deck unknown | Engineering Services Risks | Low | High
67 | For projects involving bridge removal, bridge carries traffic during staging | Engineering Services Risks | Low | High
68 | Verify that all seasonal constraints and permitting requirements are identified and incorporated in the project schedule | Engineering Services Risks | Low | High
69 | Complex structures hydraulic design requiring investigation and planning | Engineering Services Risks | Medium | Low
70 | Assumptions upon which the Advance Planning Study is based on are realistic and verification of these assumptions prior to completion of the Project Report | Engineering Services Risks | High | Low
71 | Design changes to alignment, profile, typical cross section, stage construction between Advance Planning Study and the Bridge Site Submittal | Engineering Services Risks | High | Medium
72 | Unexpected environmental constraints that impact bridge construction | Engineering Services Risks | Low | Medium
73 | Unforeseen aesthetic requirements | Engineering Services Risks | Low | High
74 | Delay due to permits or agreements, from Federal, State, or local agencies for geotechnical subsurface exploration | Engineering Services Risks | Low | Very high
75 | Delay due to Right-of-Entry agreements for geotechnical subsurface exploration | Engineering Services Risks | Medium | Medium
76 | Delay due to traffic management and lane closure for geotechnical subsurface exploration | Engineering Services Risks | Medium | High
77 | Utility relocation requires more time than planned | Right of Way Risks | High | Low
78 | Unforeseen railroad involvement | Right of Way Risks | Low | High
79 | Resolving objections to Right of Way appraisal takes more time and/or money | Right of Way Risks | High | Medium
80 | Right of Way datasheet incomplete or underestimated | Right of Way Risks | Medium | Medium
81 | Need for “Permits to Enter” not considered in project schedule development | Right of Way Risks | High | Medium
82 | Condemnation process takes longer than anticipated | Right of Way Risks | High | Medium
83 | Acquisition of parcels controlled by a State or Federal Agency may take longer than anticipated | Right of Way Risks | Medium | Low
84 | Discovery of hazardous waste in the right of way phase | Right of Way Risks | Low | Low
85 | Seasonal requirements during utility relocation | Right of Way Risks | Medium | Low
86 | Utility company workload, financial condition or timeline | Right of Way Risks | Medium | Medium
87 | Expired temporary construction easements | Right of Way Risks | Medium | Low
88 | Inadequate pool of expert witnesses or qualified appraisers | Right of Way Risks | Medium | Medium
89 | Inaccurate contract time estimates | Construction Risks | Low | Medium
90 | Permit work window time is insufficient | Construction Risks | Medium | Low
91 | Change requests due to differing site conditions | Construction Risks | High | High
92 | Temporary excavation and shoring system design is not adequate | Construction Risks | High | Very high
93 | Falsework design is not adequate | Construction Risks | High | Very high
94 | Unidentified utilities | Construction Risks | Low | Medium
95 | Buried man-made objects/unidentified hazardous waste | Construction Risks | Medium | Low
96 | Dewatering is required due to change in water table | Construction Risks | Medium | Very high
97 | Temporary construction easements expire | Construction Risks | Low | Very high
98 | Electrical power lines not seen and in conflict with construction | Construction Risks | Low | Very high
99 | Street or ramp closures not coordinated with local community | Construction Risks | High | Low
100 | Insufficient or limited construction or staging areas | Construction Risks | High | Low
101 | Changes during construction require additional coordination with resource agencies | Construction Risks | Medium | Low
102 | Late discovery of aerially deposited lead | Construction Risks | Medium | Low
103 | Experimental or research features incorporated | Construction Risks | Low | Medium
104 | Unexpected paleontology findings | Construction Risks | Medium | Very high
105 | Delay in demolition due to sensitive habitat requirements or other reasons | Construction Risks | High | High
106 | Long lead time for utilities caused by design and manufacture of special components (steel towers or special pipe) | Construction Risks | High | Low
107 | Project purpose and need is not well-defined | Project Management Risks | High | Medium
108 | Project scope definition is incomplete | Project Management Risks | Low | High
109 | Project scope, schedule, objectives, cost, and deliverables are not clearly defined or understood | Project Management Risks | Medium | High
110 | No control over staff priorities | Project Management Risks | Low | Medium
111 | Consultant or contractor delays | Project Management Risks | Low | High
112 | Estimating and/or scheduling errors | Project Management Risks | Low | High
113 | Unplanned work that must be accommodated | Project Management Risks | Low | Very high
114 | Lack of coordination/communication | Project Management Risks | Medium | Medium
115 | Underestimated support resources or overly optimistic delivery schedule | Project Management Risks | Low | Low
116 | Scope creep | Project Management Risks | High | Very high
117 | Unresolved project conflicts not escalated in a timely manner | Project Management Risks | Low | Very high
118 | Unanticipated escalation in right of way values or construction cost | Project Management Risks | High | Medium
119 | Delay in earlier project phases jeopardizes ability to meet programmed delivery commitment | Project Management Risks | High | Low
120 | Added workload or time requirements because of new direction, policy, or statute | Project Management Risks | High | High
121 | Local agency support not attained | Project Management Risks | Low | Very high
122 | Public awareness/campaign not planned | Project Management Risks | High | Medium
123 | Unforeseen agreements required | Project Management Risks | Medium | High
124 | Priorities change on existing program | Project Management Risks | Medium | Very high
125 | Inconsistent cost, time, scope, and quality objectives | Project Management Risks | Medium | Very high
126 | Inexperienced staff assigned | Organizational Risks | Low | High
127 | Losing critical staff at crucial point of the project | Organizational Risks | High | High
128 | Insufficient time to plan | Organizational Risks | High | Low
129 | Unanticipated project manager workload | Organizational Risks | Medium | Low
130 | Internal “red tape” causes delay getting approvals, decisions | Organizational Risks | High | Medium
131 | Functional units not available, overloaded | Organizational Risks | Low | High
132 | Lack of understanding of complex internal funding procedures | Organizational Risks | Medium | High
133 | Priorities change on existing program | Organizational Risks | High | High
134 | Inconsistent cost, time, scope and quality objectives | Organizational Risks | Low | Very high
135 | Overlapping of one or more project limits, scope of work or schedule | Organizational Risks | Low | Very high
136 | Funding changes for fiscal year | Organizational Risks | Medium | Very high
137 | Lack of specialized staff (biology, anthropology, geotechnical, archeology, etc.) | Organizational Risks | Low | Low
138 | Capital funding unavailable for right of way or construction | Organizational Risks | Medium | Low
139
140
141
142
143
144
145
146
147
148
149
150

## Control
Control
Types
Construction Risks
Design Risks
Engineering Services Risks
Environmental Risks
External Risks
Organizational Risks
Project Management Risks
Right of Way Risks
All
Last entry (all) | 9
Selection | 9
Selection (name) | All
Impacts
Low
Medium
High
Probabilities
Low
Medium
High
Very high
Cross Table
Rows in cross table | 15
Helper Columns
Helper Col 1 | Helper Col 2
1 | Low
2 | Low
3 | Low
4 | Low
5 | Low
6 | Low
7 | Low
8 | Low
9 | Low
10 | Low
11 | Low
12 | Low
13 | Low
14 | Low
15 | Low
1 | Medium
2 | Medium
3 | Medium
4 | Medium
5 | Medium
6 | Medium
7 | Medium
8 | Medium
9 | Medium
10 | Medium
11 | Medium
12 | Medium
13 | Medium
14 | Medium
15 | Medium
1 | High
2 | High
3 | High
4 | High
5 | High
6 | High
7 | High
8 | High
9 | High
10 | High
11 | High
12 | High
13 | High
14 | High
15 | High